## Sheet1
	Eintrittswahrscheinlichkeit					max. Schaden					Gewichteter Schaden
Risiko-ID	Architecture	Prototype	Milestone1	Milestone2	Milestone3	Completion	Release BA	Architecture	Prototype	Milestone1	Milestone2	Milestone3	Completion	Release BA	Architecture	Prototype	Milestone1	Milestone2	Milestone3	Completion	Release BA
Risiko 1	50%	50%	10%	0%	0%	0%	0%	50 h	50 h	50 h	50 h	50 h	50 h	50 h	25 h	25 h	5 h	0 h	0 h	0 h	0 h
Risiko 2	25%	25%	10%	0%	0%	0%	0%	16 h	16 h	16 h	16 h	16 h	16 h	16 h	4 h	4 h	2 h	0 h	0 h	0 h	0 h
Risiko 3	25%	10%	10%	10%	10%	10%	10%	16 h	40 h	40 h	40 h	40 h	40 h	40 h	4 h	4 h	4 h	4 h	4 h	4 h	4 h
Risiko 4	25%	25%	25%	25%	25%	25%	25%	16 h	16 h	16 h	16 h	16 h	16 h	16 h	4 h	4 h	4 h	4 h	4 h	4 h	4 h
Risiko 5		50%	50%	40%	30%	20%	10%		16 h	16 h	16 h	16 h	16 h	16 h		8 h	8 h	6 h	5 h	3 h	2 h
	25.09.14	06.10.14	13.10.14

Risiko 1	A	P	M1	M2	M3	C	R
Eintrittswahr-scheinlichkeit	50%	50%	10%	0%	0%	0%	0%
max. Schaden	50 h	50 h	50 h	50 h	50 h	50 h	50 h
Gewichteter Schaden	25 h	25 h	5 h	0 h	0 h	0 h	0 h

Risiko 2	A	P	M1	M2	M3	C	R
Eintrittswahr-scheinlichkeit	25%	25%	10%	0%	0%	0%	0%
max. Schaden	16 h	16 h	16 h	16 h	16 h	16 h	16 h
Gewichteter Schaden	4 h	4 h	2 h	0 h	0 h	0 h	0 h

Risiko 3	A	P	M1	M2	M3	C	R
Eintrittswahr-scheinlichkeit	25%	10%	10%	10%	10%	10%	10%
max. Schaden	16 h	40 h	40 h	40 h	40 h	40 h	40 h
Gewichteter Schaden	4 h	4 h	4 h	4 h	4 h	4 h	4 h

Risiko 4	A	P	M1	M2	M3	C	R
Eintrittswahr-scheinlichkeit	25%	25%	25%	25%	25%	25%	25%
max. Schaden	16 h	16 h	16 h	16 h	16 h	16 h	16 h
Gewichteter Schaden	4 h	4 h	4 h	4 h	4 h	4 h	4 h

Risiko 5	A	P	M1	M2	M3	C	R
Eintrittswahr-scheinlichkeit		50%	50%	40%	30%	20%	10%
max. Schaden		16 h	16 h	16 h	16 h	16 h	16 h
Gewichteter Schaden		8 h	8 h	6 h	5 h	3 h	2 h
Eintrittswahrscheinlichkeit
max. Schaden